## Slide 1: Inter-Ministerial Committee on Capital Dredging for Major Ports
Ist Meeting
12th March 2012
Yojana Bhawan

## Slide 2: Draft at Indian Ports
Low Drafts at Indian Ports
  Range between 7 mts in old ports to 17 mts in new ports
  Implication of lower Draft: Higher parcel Size vessels cannot be accommodated
  True especially for bulk commodities such as coal and also of containers
  Need to Increase the draft to 14 mts in all ports and to 17 mts in the proposed hub ports of Chennai and Vizag on east coast and JNPT and Cochin on the west coast

## Slide 3: Dredging
Capital Dredging is undertaken either to create new channels, basins, berths etc. or to deepen the existing infrastructure
Maintenance dredging is carried out to maintain the depth of existing infrastructure

## Slide 4: Dredging in the 11th Plan by Major Ports: Targets and Achievements
Targets (Million Cubic Metres) |  |  | Achievements (Million Cubic Metres) |  | 
Capital | Maintenance | Total | Capital | Maintenance | Total
298.28 | 380.06 | 678.34 | 95.36 | 261.83 | 357.19
Major Ports achieved only 32% of targeted quantity in capital
dredging and 69% of Maintenance dredging .
Shortfall in achievement due to many factors such as failure
to take up a number of port development projects; environmental constraints; requirement of carrying out engineering studies; poor response of bidders and financial constraints.

## Slide 5: Port-Wise Expenditure on Capital and Maintenance Dredging : First Four Years of 11th Plan (Rs Crore)
PORT | 2007-08 | 2008-09 | 2009-10 | 2010-11 $
Kolkata | 324.87 | 345.66 | 417.18 | 403.96
Paradip | 28.38 | 39.97 | 42.47 | 43.51
Vishakhapatnam | 15.00 | 9.33 | 16.14 | 21.74
Ennore | 7.20 | 9.79 | 0.08 | -
Chennai | - | 0.41 | - | -
V.O. Chidambarnar | - | - | - | -
Cochin | 44.18 | 50.58 | 139.37 # | 224.84 #
New Mangalore | 25.64 | 22.51 | 39.39 | 37.98
Mormugao | 17.38 | 21.80 | 26.90 | 22.02
Mumbai | 28.66 | 51.30 | 25.64 | 22.00
JNPT | 9.69 | 22.12 | 24.14 | 18.52
Kandla | 53.22 | 96.39 | 99.15 | 66.08
Total | 554.22 | 669.86 | 830.46 | 860.65

## Slide 6: Port-Wise Cost of Dredging in 11th Plan
Separate expenditure figures for capital and maintenance dredging were not readily available. A rough indicator of the expenditure on capital dredging in the 11th Plan can be obtained by assuming the dredging expenditure in 2011-12 to be the same as 2010-11 and then taking the pro rata based on quantity of capital dredging as a proportion of total dredging which comes to nearly 1008 crores (Out of total estimated expenditure on dredging of 3775 crores).
Maximum dredging expenditure is incurred at Kolkata/Haldia. Kolkata port has another dredging related expenditure which is called River Running (RR) Scheme on which the 11th plan outlay was 375 crores (provided under GBS) but the expenditure was nil.
GBS support was extended to Cochin port to the extent of 80.44 crores and 149.75 crores in 2009-10 and 2010-11.

## Slide 7: Targets for Dredging for the 12th Plan : Major Ports
Targets for Dredging for the 12th Plan : Major Ports (Million Cubic Metres) |  | 
Capital | Maintenance | Total
221.11 | 404.35 | 625.46
This shows that the capital dredging requirement projected in 12th plan is less than the target for the 11th plan (292.28) but more than the achievements of the 11th plan (95.36). The 12th plan dredging target if achieved will enable all the major ports (except Kolkata) to handle vessels with 14 mtr draft at the end of the 12th plan period.

## Slide 8: Projections of Dredging at Major Ports: 12th Plan
Port | Qty Dredg Rqd MCM |  | Fund Rqd Capital Dredg, Rs Cr |  |  | Total | R & S
 | Cap | Maint | IR | GBS | EBR |  | 
Kolkataa | 20.88 | 111.00 | 0 | 1020.22 | 0 | 1020.22 | 1072.64
Paradeep | 14.85 | 30.0 | 45.80 | 93 | 0 | 138.80 | 1357.97
Vishakhapatnam | 15.35 | 3.75 | 869.91 | 0 | 0 | 869.91 | 279.13
Ennore Port | 17.50 | 3.0 | 0 | 570 | 30 | 600 | 226.89
Chennai Port | 16.65 | 6.0 | 70 | 73 | 0 | 143 | 1121.69
V. O. Chedambernaar (Tuticorin Port) | 27.48 | ---- | 971 | 0 | 1797 | 2768 | 423.69
Cochin | 9.5 | 90.0 | 35 | 210 | 0 | 245 | (-)380.74
New Mangalore | 4.50 | 30.50 | 60 | 330 | 0 | 390 | 384.10
Marmurgao Port | 14.0 | 20.0 | 15 | 600 | 0 | 615 | 154.79
JNPT | 54.75 | 18.9 | 1300 | 0 | 0 | 1300 | 2829.34
Mumbai Port | 9.45 | 21.5 | 162 | 0 | 0 | 162 | (-)380.36
Kandla Port Trust | 15.10 | 45.50 | 585 | 0 | 0 | 585 | 780.78
Total | 221.11 | 404.25 | 4113.71 | 2896.22 | 1827 | 8836.93 | 7869.92

## Slide 9: Funds for Dredging
The total funding requirement for capital dredging at major ports is 8836.93 crore which is proposed to be funded to the extent of 4113.71 crore from internal generation, 2896.22 crore from GBS and 1827 crore from EBR.
The maximum funding is required at Tuticurin port which is proposed to be financed by internal revenue and EBR; at JNPT the entire funding is proposed to be met from internal generation. GBS requirement of 1020 crore has been projected for the River Running scheme at Kolkata/Haldia, which in the nature of maintenance dredging but which has been historically being provided out of GBS. Some of the other ports which have projected substantial funding for capital dredging from GBS are Marmugao, Ennore, New Mangalore and Cochin.

## Slide 10: Ministry of Shipping’s Suggestion
Ministry of Shipping has suggested that in line with international practice where the cost of dredging the channel and berth is funded either by the municipal government owning the port or the federal government, the central government may consider the declaration of port channel as “National Channel” and fund capital dredging project through budgetary support till all the ports achieve 14 mtr of draft. There projects could be appraised by EFC/PIB depending upon the quantum of financial support required for each project.

## Slide 11: Other Factors need Consideration
Past Practice of Providing GBS for dredging at Kolkata Port only and to some extent to Cochin
Dredging can be financed from Reserves and Surpluses at ports
Low Dredging achievement due to non-financial factors
Capacity of dredging industry, DCI performance, operational and technological issues in dredging, time/cost overrun in dredging projects, availability of trained manpower, possibility of entering into JV with ports etc. need to be reviewed
Higher GBS for dredging, if approved, should translate to arrival of higher capacity vessels in Indian ports
Port Charges, especially Vessel Related Charges which are currently high due to inclusion of dredging cost in tariff computation, should also come down – Quantification of these advantages would be required.
Alternative financing mechanisms such as PPP in dredging need to be explored
Environmental factors – EIA notification 2006 and CRZ notification 2011 require state government and MOEF approval for all dredging projects. Ministry of Shipping’s proposal to speed up this process pending with MoEF.

## Slide 12: Terms of Reference of the IMC
To estimate the dredging cost (capital and recurring) of maintaining draft at all major ports at 17 metres.
To assess the impact of capital dredging on traffic, port charges, investment in port equipment, etc.
To assess the financial ability of ports to meet the dredging costs.
To evaluate financial alternatives for meeting dredging costs, including debt instruments, PPP, etc.
To assess the capacity of Dredging Corporation of India (DCI) to meet additional dredging requirements.
To compare the average dredging cost of DCI with dredging costs of chartering dredgers.
To find out the best international practices in dredging.
Any other issue.